## Product backlog
Item |  |  | Status | Priority | Estimation(Hours : Day) | Sprint | Release
As a Student
Registration
|  | Userstory 1.1 | Completed | Very High |  | 1 | 2021-02-19
Profile
|  | Userstory 1.2 | In progress | High |  | 2
|  | Userstory 1.3 | In progress | High |  | 2
|  | Userstory 1.4 | In progress | High |  | 2
Ratings
|  | Userstory 1.5 | Not done | Low
Chat
|  | Userstory 1.6 | Not done | Low
|  | Userstory 1.7 | Not done | Low
List Services
|  | Userstory 1.8 | Not done | Low
|  | Userstory 1.12 | Not done | Midium |  | 4
|  | Userstory 1.13 | Not done | Midium
Login
|  | Userstory 1.9 | Completed | Very High |  | 1 | 2021-02-19
|  | Usersroty 1.10 | Not done | Midium
Logout
|  | Userstory 1.11 | Completed | Very High |  | 1 | 2021-02-19
SSL
|  | Userstory 1.14 | Not done | Midium |  | 3
Giving flag
|  | Userstory 1.15 | Not done | Midium |  | 3
Filter
|  | Userstory 1.16 | In progress | High |  | 2
As a Small Business
Registration
|  | Userstory 2.1 | Completed | Very High |  | 1 | 2021-02-19
Profile
|  | Userstory 2.2 | Not done | High |  | 3
|  | Userstory 2.3 | Not done | High |  | 3
|  | Userstory 2.4 | Not done | High |  | 3
Chat
|  | Userstory 2.5 | Not done | Low
|  | Userstory 2.7 | Not done | Low
List Requirements
|  | Userstory 2.6 | Not done | Low
|  | Userstory 2.11 | Not done | Midium |  | 4
|  | Userstory 2.12 | Not done | High |  | 3
Login
|  | Userstory 2.8 | Completed | Very High |  | 1 | 2021-02-19
|  | Userstory 2.9 | Not done | Midium
Logout
|  | Userstory 2.10 | Completed | Very High |  | 1 | 2021-02-19
SSL
|  | Userstory 2.13 | Not done | Midium |  | 3
As an Agency
|  | Userstory 3.1 | Not done | Low |  | 4
|  | Userstory 3.2 | Not done | Low

## Story Points
Items(Userstory and tasks) |  |  | Story points | Describe | To be implemented or not in this semester | Story points
As a Student
| Registration |  |  |  |  | 1
|  | Userstory 1.1 | 1 | not simple, but a member had a knowledge | Yes | 2
|  | Userstory 1.2 | 2 | predictable 1~2 days | Yes | 13 | 3
|  | Userstory 1.3 | 2 | predictable 1~2 days | Yes | 8 | 5
|  | Userstory 1.4 | 1 | more easier than 1.2 and 1.3 | Yes | 5 | 8
| Ratings |  |  |  |  | 3 | 13
|  | 5. As a student I want to rate certain profile, so that they get review. | 13 | Method, implementation logic are uncertain, We do not have knowledge | No | 40 | 40
Chat
|  | Userstory 1.6 | 8 | logic are uncertain, need to implement UI, and two id should be identified | No
|  | Userstory 1.7 | 8 | logic are uncertain, need to implement UI, and two id should be identified | No
List Services
|  | Userstory 1.8 | 5 | requirement are not decided | Yes
|  | Userstory 1.12 | 3 | it can be supposed that more easier than 1.8 | Yes
|  | Userstory 1.13 | 8 | need to consider how we can upload sound and images | No
Login
|  | Userstory 1.9 | 1 | not simple, but a member had a knowledge | Yes
|  | Usersroty 1.10 | 5 | logic are uncertain | No
Logout
|  | Userstory 1.11 | 1 | not simple, but a member had a knowledge | Yes
SSL
|  | Userstory 1.14 | 2 | predictable 1day | Yes
Giving flag
|  | Userstory 1.15 | 8 | Method are uncertain, We need to breakdown tasks | Yes
Filter
|  | Userstory 1.16 | 3 | logic are uncertain but a member had a knowledge | Yes
As a Small Business
Registration
|  | Userstory 2.1 | 1 | not simple, but a member had a knowledge | Yes
|  | Userstory 2.2 | 2 | predictable 1~2 days | Yes
|  | Userstory 2.3 | 2 | predictable 1~2 days | Yes
|  | Userstory 2.4 | 1 | more easier than 1.2 and 1.3 | Yes
Chat
|  | Userstory 2.5 | 8 | logic are uncertain, need to implement UI, and two id should be identified | No
|  | Userstory 2.6 | 8 | logic are uncertain, need to implement UI, and two id should be identified | No
List Requirements
|  | Userstory 2.7 | 5 | requirement are not decided | Yes
|  | Userstory 2.11 | 3 | it can be supposed that more easier than 1.8 | Yes
|  | Userstory 2.12 | 8 | need to consider how we can upload sound and images | No
Login
|  | Userstory 2.8 | 1 | not simple, but a member had a knowledge | Yes
|  | Userstory 2.9 | 5 | logic are uncertain | No
Logout
|  | Userstory 2.10 | 1 | not simple, but a member had a knowledge | Yes
SSL
|  | Userstory 2.13 | 2 | predictable 1day | Yes
As an Agency
|  | Userstory 3.1 | 5 | need dashboard page and logic to count number of matching | Yes
|  | Userstory 3.2 | 40 | uncertain logic and what "trustworth" is | No

## User story
1. Student:
Registration:
1. As a student I want to register, so that I can make my profile.
2. As a student I want to create my profile, so that I can show my skills to recruiters.
3. As a student I want to update my profile, so that I can add new skills services.
4. As a student I want to delete my profile because I don’t want to be a member of student skill platform.
Ratings:
5. As a student I want to rate certain profile, so that they get review.
Chat:
6. As a student I want to chat to recruiters, so that I can introduce my skills recruiters.
7. As a student I want to ask questions, so that I can offer my skills.
List services:
8. As a student I want to list my services, so that I can provide short profile.
Log-in:
9. As a student I want to log-in to the system, so that I can see any information.
10. As a student I want to set password, so that I can issue new password.
Log-out:
11. As a student I want to log-out from the system, so that I can be out from system.
List services:
12. As a student I want to remove, so that we delete my short profile.
13. As a student I want to upload every sorts of portfolio so that I can show my skill
SSL:
14. As a student, I want to protect our sensitive data, so that I can use this platform at ease.
Giving flag:
15. As a student I want to flag to a project that I am interested in, so that I can be matched with businesses.
Filter:
16. As a student I want to search any projects that related to my domain and skills, so that it can be easier to match with businesses.
2. Recruiter:
Registration:
1. As a recruiter I want to register, so that we can make my profile.
2. As a recruiter I want to create our profile, so that we can list our requirements.
3. As a recruiter I want to update our profile, so that we can add new requirements.
4. As a recruiter I want to delete our profile because we don’t want to be a member of student skill platform.
Chat:
5. As a recruiter I want to chat to students, so that we see the skills they provide.
6. As a recruiter I want to ask questions to students, so that we can purchase student services.
List requirements:
7. As a recruiter I want to list requirements, so that we can provide short profile.
Log-in:
8. As a recruiter I want to log-in to the system, so that I can see any information.
9. As a recruiter I want to set password, so that I can issues new password.
Log-out:
10. As a recruiter I want to log-out from the system, so that I can be out from system.
List requirements:
11. As a recruiter I want to remove, so that we delete my short profile.
Project:
12. As a recruiter I want to advertise project so that I can get a person for our project
SSL:
13. As a recruiter, I want to protect our sensitive data, so that I can use this platform at ease.
3. Agency
1. As an Agency, I want to see how many students has been matched with recruiters, so that I can check the number.
2. As an Agency, I want to check whether the companies that registered the system is trustable, so that I can be relieved.

## Sprint1
Items(Userstory and tasks) |  | Status | Priority | Estimation(Hours) | Assined member
Userstory 1.1
| Page layout | Completed |  | 2 | Kazuki
| Reseach / Training | Completed |  | 2 | Imran
| Database setup | Completed |  | 1 | Imran,Deekshith,Kazuki
| PHP setup | Completed |  | 1 | Imran,Deekshith,Kazuki
| Implement code | Completed |  | 2 | Imran
| Testing | Completed |  | 2 | Deekshith
Userstory 1.9
| Page layout(login-page) | Completed |  | 2 | Kazuki
| Page layout(welcome-page) | Completed |  | 2 | Imran
| Reseach / Training | Completed |  | 1 | Imran
| Implement code(welcome-page apearance) | Completed |  | 2 | Imran
| Implement code(login logic and appearance) | Completed |  | 2 | Imran
| Testing | Completed |  | 2 | Deekshith
Userstory 1.11
| Page layout(logout-page) | Completed |  | 2 | Kazuki
| Reseach / Training | Completed |  | 1 | Imran
| Implement code | Completed |  | 2 | Imran
| Testing | Completed |  | 2 | Deekshith
Userstory 2.1
| Page layout | Completed |  | 1 | Kazuki
| Reseach / Training | Completed |  | 1 | Imran
| Implement code | Completed |  | 2 | Imran
| Testing | Completed |  | 2 | Kazuki
Userstory 2.8
| Page layout(login-page) | Completed |  | 1 | Kazuki
| Page layout(welcome-page) | Completed |  | 2 | Imran
| Implement code(welcome-page apearance) | Completed |  | 2 | Imran
| Implement code(login logic and appearance) | Completed |  | 2 | Imran
| Testing | Completed |  | 2 | Kazuki
Userstory 2.10
| Page layout(logout-page) | Completed |  | 1 | Kazuki
| Implement code | Completed |  | 2 | Imran
| Testing | Completed |  | 2 | Kazuki

## Sprint2
Items(Userstory and tasks) |  | Status | Priority | Estimation(Hours) | Assined member
Userstory 1.2
| Decide User Interface | In progress |  | 4 | Imran
| Implementation | In progress |  | 4 | Imran
| Testing | Not done |  | 3 | Deekshith
Userstory 1.3
| Implementation | In progress |  | 4 | Imran
| Testing | Not done |  | 3 | Deekshith
Userstory 1.4
| Implementation | In progress |  | 4 | Imran
| Testing | Not done |  | 3 | Kazuki
Userstory 1.16
| Implementation | In progress |  | 4 | Imran
| Testing | Not done |  | 3 | Kazuki